## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | Work Product Cross Reference/Details sheet | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | FMS_01 | manage user | M | US:101 | user can login into the system and either as admin or as User perform its operations | Admin/ User | Flight Management System | medium | analysing the work flow of project and handling rest api | Taken reference from case study and documentation | admin/user will access or provides the resurces to perform the required operation | [5 empty] | required |  | this is to add user ,delete,update the user and perform user operations,.
2 | FMS_02 | manage passenger | M | US:102 | user provides the passenger details for which flight is booked | User | Flight Management System | medium | analysing the work flow of project and handling rest api | Taken reference from case study and documentation | admin will access the resurces from fromtend as provided by user after booking and stored in the passenger database | [5 empty] | required |  | this is to manage passenger details
3 | FMS_03 | Booking Flight | M | US:103 | user will view,select the flight,airport to be booked,add the passenger details | User | Flight Management System | medium | analysing the work flow of project and handling rest api | Taken reference from case study and documentation | user will access the resurces from backend to perform the required operation | [5 empty] | required |  | this to book ,cancel the booking of flight
4 | FMS_04 | manage airport | M | US:104 | Admin can login into the system amd manages the airport details . | Admin | Flight Management System | medium | analysing the work flow of project and handling rest api | Taken reference from case study and documentation | admin will access the resources from backend to manage operations on airport details. | [5 empty] | required |  | for airport management
5 | FMS_05 | manage schedule of flight | M | US:105 | admin can login into the system and changes the schedule of flight as required. | Admin | Flight Management System | medium | analysing the work flow of project and handling rest api | Taken reference from case study and documentation | admin will access and f lights scheduling(change in time or date) management is done . | [5 empty] | required |  | this to manage flight scheduling details
6 | FMS_06 | manage flight | M | US:106 | admin can login into the system and manages the flight details | Admin | Flight Management System | medium | analysing the work flow of project and handling rest api | Taken reference from case study and documentation | Managing the flight details for booking the flight | [5 empty] | required |  | flight details management
7 | 7
8 | 8
9 | 9
10 | 10
11 | 11
12 | 12
13 | 13
14 | 14
Sprint 1 | Sprint 1
15 | 15
16 | 16
17 | 17
18 | 18
19 | 19
20 | 20
21 | 21
22 | 22
23 | 23
24 | 24
25 | 25
26 | 26
27 | 27
28 | 28
29 | 29
30 | 30
31 | 31
32 | 32
33 | 33
34 | 34
35 | 35
36 | 36
37 | 37
38 | 38
39 | 39
40 | 40
41 | 41
42 | 42
43 | 43
44 | 44
45 | 45
46 | 46
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.

## Sprint Backlog (Scrum)
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
FMS_01 | US:101 | 1 | Understanding the microservices concepts for project implementation. | Anushka Soni | 2020-05-02 | 2 days | 2 days | completed | 2 days | Learned the microservices from the trainers
|  | 2 | Created a git repository and understanding the team to work with git and analysis of case study and concepts of spring,requiremnet specification,agile concepts | Anushka Soni | 2020-05-04 | 1day | 1 day | completed | 1 day | A common git repository is created for collaboration among teammates and studied use cases,class diagram and their implementations to get better understanding
|  | 3 | Designed class diagram,use cases,ER diagram | Anushka Soni | 2020-05-05 | 1 day | 1 day | completed | 1 day | Observed the digaram and case studies ,according to it, test cases and pojo classes are created
|  | 4 | Test cases was implemented | Anushka Soni | 2020-05-06 | 1day | 1day | completed | 1 day | prepared all the test cases involved in module
|  | 5 | Created pojo classes for modules ,entities design involved in modules . | Anushka Soni | 2020-05-07 | 1 day | 1 day | completed | 1 day | Implemeted all the classes and packages with specified details provided in the documentation
|  | 6 | All the crud operations are Implementedand user defined exception for the individual module | Anushka Soni | 2020-05-08 | 1 day | 1 day | completed | 1 day | Performed all the crud operations using Layered wise architecture and exception are also implemented
|  | 7 | creation of rest controller,endpoints+validations, testing with postman | Anushka Soni | 2020-05-11 | 1 day | 1 day | completed | 1 day | mplemented all the RESTAPIs and tested their working
|  | 8 | Angular UI , created angular components required in the assigned module, forms handling | Anushka Soni | 2020-05-12 | 1 day | 1 day | completed | 1 day | We have used Angular6+
|  | 9 | Angular UI , created angular components required in the assigned module, forms handling with validations | Anushka Soni | 2020-05-13 | 1 day | 1 day | completed | 1 day | We have used Angular6+
|  | 10 | Angular UI, Introduced Service class which will interact with server side using httpclient ,observables can now be subscribed in components | Anushka Soni | 2020-05-14 | 1 day | 1 day | completed | 1 day | We have used Angular6+ ,Interacted with server side java
|  | 11 | Angular UI, Introduced Service class which will interact with server side using httpclient ,observables can now be subscribed in components | Anushka Soni | 2020-05-15 | 1 day | 1 day | completed | 1 day | We have used Angular6+ ,Interacted with server side java
|  | 12 | Individual server side modules are being converted into microservices,Discovery client is created | Anushka Soni | 2020-05-16 | 1 day | 1 day | completed | 1 day | Discovery server is created for converting server side modules into microservices.
|  | 13 | code debugging and fixing is performed | Anushka Soni | 2020-05-18 | 1 day | 1 day | completed | 1 day | Bug fixing is done for proper flow
|  | 14 | code debugging and Client side desiging improvement | Anushka Soni | 2020-05-19 | 1 day | 1 day | completed | 1 day | Clent side desiging is improved
FMS_02 | US:102 | 1 | Understanding the microservices for project implementation | Anushka Soni | 2020-05-02 | 2 days | 2 days | completed | 2 days | Learned the microservices from the trainers
|  | 2 | Created a git repository and understanding the team to work with git and analysis of case study and concepts of spring,requiremnet specification,agile concepts | Anushka Soni | 2020-05-04 | 1 day | 1 day | completed | 1 day | A common git repository is created for collaboration among teammates and studied use cases,class diagram and their implementations to get better understanding
|  | 3 | Designed class diagram,use cases,ER diagram | Anushka Soni | 2020-05-05 | 1 day | 1 day | completed | 1 day | Observed the digaram and case studies ,according to it, test cases and pojo classes are created
|  | 4 | Test cases was implemented | Anushka Soni | 2020-05-06 | 1 day | 1 day | completed | 1 day | prepared all the test cases involved in module
|  | 5 | Created pojo classes for modules ,entities design involved in modules with it | Anushka Soni | 2020-05-07 | 1 day | 1 day | completed | 1 day | Implemeted all the classes and packages with specified details provided in the documentation
|  | 6 | All the crud operations are Implementedand user defined exception for the individual module. | Anushka Soni | 2020-05-08 | 1 day | 1 day | completed | 1 day | Performed all the crud operations using Layered wise architecture and exception are also implemented
|  | 7 | creation of rest controller,endpoints+validations, testing with postman | Anushka Soni | 2020-05-11 | 1 day | 1 day | completed | 1 day | mplemented all the RESTAPIs and tested their working
|  | 8 | Angular UI , created angular components required in the assigned module, forms handling | Anushka Soni | 2020-05-12 | 1 day | 1 day | completed | 1 day | We have used Angular6+
|  | 9 | Angular UI , created angular components required in the assigned module, forms handling with validations | Anushka Soni | 2020-05-13 | 1 day | 1 day | completed | 1 day | We have used Angular6+
|  | 10 | Angular UI, Introduced Service class which will interact with server side using httpclient ,observables can now be subscribed in components | Anushka Soni | 2020-05-14 | 1 day | 1 day | completed | 1 day | We have used Angular6+ ,Interacted with server side java
|  | 11 | Angular UI, Introduced Service class which will interact with server side using httpclient ,observables can now be subscribed in components | Anushka Soni | 2020-05-15 | 1 day | 1 day | completed | 1 day | We have used Angular6+ ,Interacted with server side java
|  | 12 | Individual server side modules are being converted into microservices,Discovery client is created | Anushka Soni | 2020-05-16 | 1 day | 1 day | ompleted | 1 day | Discovery server is created for converting server side modules into microservices.
|  | 13 | code debugging and fixing is performed | Anushka Soni | 2020-05-18 | 1 day | 1 day | completed | 1 day | Bug fixing is done for proper flow
|  | 14 | code debugging and Client side desiging improvement | Anushka Soni | 2020-05-19 | 1 day | 1 day` | completed | 1 day | Clent side desiging is improved
FMS_03 | US:103 | 1 | Understanding the microservices for project implementation | Shivam Amravanshi | 2020-05-02 | 2 days | 2 days | completed | 2 days | Learned the microservices from the trainers
|  | 2 | Created a git repository and understanding the team to work with git and analysis of case study and concepts of spring,requiremnet specification,agile concepts | Shivam Amravanshi | 2020-05-04 | 1 day | 1 day | completed | 1 day | A common git repository is created for collaboration among teammates and studied use cases,class diagram and their implementations to get better understanding
|  | 3 | designed class diagram,use cases,ER diagram | Shivam Amravanshi | 2020-05-05 | 1 day | 1 day | completed | 1 day | Observed the digaram and case studies ,according to it, test cases and pojo classes are created
|  | 4 | Test cases was implemented | Shivam Amravanshi | 2020-05-06 | day | 1 day | completed | 1 day | prepared all the test cases involved in module
|  | 5 | Created pojo classes for modules ,entities design involved in modules with it | Shivam Amravanshi | 2020-05-07 | 1 day | 1 day | completed | 1 day | Implemeted all the classes and packages with specified details provided in the documentation
|  | 6 | Implemented user defined exception for the individual module | Shivam Amravanshi | 2020-05-08 | 1 day | 1 day | completed | 1 day | Performed all the crud operations using Layered wise architecture and exception are also implemented
|  | 7 | creation of rest controller,endpoints+validations, testing with postman | Shivam Amravanshi | 2020-05-11 | 1 day | 1 day | completed | 1 day | mplemented all the RESTAPIs and tested their working
|  | 8 | Angular UI , created angular components required in the assigned module, form handling | Shivam Amravanshi | 2020-05-12 | 1 day | 1 day | completed | 1 day | We have used Angular6+
|  | 9 | Angular UI , created angular components required in the assigned module, forms handling with validations | Shivam Amravanshi | 2020-05-13 | 1 day | 1 day | completed | 1 day | We have used Angular6+
|  | 10 | Angular UI, Introduced Service class which will interact with server side using httpclient ,observables can now be subscribed in components | Shivam Amravanshi | 2020-05-14 | 1 day | 1 day | completed | 1 day | We have used Angular6+ ,Interacted with server side java
|  | 11 | Angular UI, Introduced Service class which will interact with server side using httpclient ,observables can now be subscribed in components | Shivam Amravanshi | 2020-05-15 | 1 day | 1 day | completed | 1 day | We have used Angular6+ ,Interacted with server side java
|  | 12 | Individual server side modules are being converted into microservices,Discovery client is created | Shivam Amravanshi | 2020-05-16 | 1 day | 1 day | completed | 1 day | Discovery server is created for converting server side modules into microservices.
|  | 13 | code debugging and fixing is performed | Shivam Amravanshi | 2020-05-18 | 1 day | 1 day | completed | 1 day | Bug fixing is done for proper flow
|  | 14 | code debugging and Client side desiging improvement | Shivam Amravanshi | 2020-05-19 | 1 day | 1 day | completed | 1 day | Clent side desiging is improved
FMS_04 | US:104 | 1 | Understanding the microservices for project implementation | Shivam Amravanshi | 2020-05-02 | 2 days | 2 days | completed | 2 days | Learned the microservices from the trainers
|  | 2 | Created a git repository and understanding the team to work with git and analysis of case study and concepts of spring,requiremnet specification,agile concepts | Shivam Amravanshi | 2020-05-04 | 1 day | 1 day | completed | 1 day | A common git repository is created for collaboration among teammates and studied use cases,class diagram and their implementations to get better understanding
|  | 3 | designed class diagram,use cases,ER diagram | Shivam Amravanshi | 2020-05-05 | 1 day | 1 day | completed | 1 day | Observed the digaram and case studies ,according to it, test cases and pojo classes are created
|  | 4 | Test cases was implemented | Shivam Amravanshi | 2020-05-06 | 1 day | 1 day | completed | 1 day | prepared all the test cases involved in module
|  | 5 | Created pojo classes for modules ,entities design involved in modules with it | Shivam Amravanshi | 2020-05-07 | 1 day | 1 day | completed | 1 day | Implemeted all the classes and packages with specified details provided in the documentation
|  | 6 | Implemented user defined exception for the individual module | Shivam Amravanshi | 2020-05-08 | 1 day | 1 day | completed | 1 day | Performed all the crud operations using Layered wise architecture and exception are also implemented
|  | 7 | creation of rest controller,endpoints+validations, testing with postman | Shivam Amravanshi | 2020-05-11 | 1 day | 1 day | completed | 1 day | mplemented all the RESTAPIs and tested their working
|  | 8 | Angular UI , created angular components required in the assigned module, forms handling | Shivam Amravanshi | 2020-05-12 | 1 day | 1 day | completed | 1 day | We have used Angular6+ ,
|  | 9 | Angular UI , created angular components required in the assigned module, forms handling with validations | Shivam Amravanshi | 2020-05-13 | 1 day | 1 day | completed | 1 day | We have used Angular6+
|  | 10 | Angular UI, Introduced Service class which will interact with server side using httpclient ,observables can now be subscribed in components | Shivam Amravanshi | 2020-05-14 | 1 day | 1 day | completed | 1 day | We have used Angular6+ ,Interacted with server side java
|  | 11 | Angular UI, Introduced Service class which will interact with server side using httpclient ,observables can now be subscribed in components | Shivam Amravanshi | 2020-05-15 | 1 day | 1 day | completed | 1 day | We have used Angular6+ ,Interacted with server side java
|  | 12 | Individual server side modules are being converted into microservices,Discovery client is created | Shivam Amravanshi | 2020-05-16 | 1 day | 1 day | completed | 1 day | Discovery server is created for converting server side modules into microservices.
|  | 13 | code debugging and fixing is performed | Shivam Amravanshi | 2020-05-18 | 1 day | 1 day | completed | 1 day | Bug fixing is done for proper flow
|  | 14 | code debugging and Client side desiging improvement | Shivam Amravanshi | 2020-05-19 | 1 day | 1 day | completed | 1 day | Clent side desiging is improved
FMS_05 | US:105 | 1 | Understanding the microservices for project implementation | Anirudh Bhardwaj | 2020-05-02 | 2 days | 2 days | completed | 2 days | Learned the microservices from the trainers
|  | 2 | Created a git repository and understanding the team to work with git and analysis of case study and concepts of spring,requiremnet specification,agile concepts | Anirudh Bhardwaj | 2020-05-04 | 1 day | 1 day | completed | 1 day | A common git repository is created for collaboration among teammates and studied use cases,class diagram and their implementations to get better understanding
|  | 3 | designed class diagram,use cases,ER diagram | Anirudh Bhardwaj | 2020-05-05 | 1 day | 1 day | completed | 1 day | Observed the digaram and case studies ,according to it, test cases and pojo classes are created
|  | 4 | Test cases was implemented | Anirudh Bhardwaj | 2020-05-06 | 1 day | 1 day | completed | 1 day | prepared all the test cases involved in module
|  | 5 | Created pojo classes for modules ,entities design involved in modules with it | Anirudh Bhardwaj | 2020-05-07 | 1 day | 1 day | completed | 1 day | Implemeted all the classes and packages with specified details provided in the documentation
|  | 6 | Implemented user defined exception for the individual module | Anirudh Bhardwaj | 2020-05-08 | 1 day | 1 day | completed | 1 day | Performed all the crud operations using Layered wise architecture and exception are also implemented
|  | 7 | creation of rest controller,endpoints+validations, testing with postman | Anirudh Bhardwaj | 2020-05-11 | 1 day | 1 day | completed | 1 day | mplemented all the RESTAPIs and tested their working
|  | 8 | Angular UI , created angular components required in the assigned module,form handling | Anirudh Bhardwaj | 2020-05-12 | 1 day | 1 day | completed | 1 day | We have used Angular6+
|  | 9 | Angular UI , created angular components required in the assigned module, forms handling with validations | Anirudh Bhardwaj | 2020-05-13 | 1 day | 1 day | completed | 1 day | We have used Angular6+
|  | 10 | Angular UI, Introduced Service class which will interact with server side using httpclient ,observables can now be subscribed in components | Anirudh Bhardwaj | 2020-05-14 | 1 day | 1 day | completed | 1 day | We have used Angular6+ ,Interacted with server side java
|  | 11 | Angular UI, Introduced Service class which will interact with server side using httpclient ,observables can now be subscribed in components | Anirudh Bhardwaj | 2020-05-15 | 1 day | 1 day | completed | 1 day | We have used Angular6+ ,Interacted with server side java
|  | 12 | Individual server side modules are being converted into microservices,Discovery client is created | Anirudh Bhardwaj | 2020-05-16 | 1 day | 1 day | completed | 1 day | Discovery server is created for converting server side modules into microservices.
|  | 13 | code debugging and fixing is performed | Anirudh Bhardwaj | 2020-05-18 | 1 day | 1 day | completed | 1 day | Bug fixing is done for proper flow
|  | 14 | code debugging and Client side desiging improvement | Anirudh Bhardwaj | 2020-05-19 | 1 day | 1 day | completed | 1 day | Clent side desiging is improved
FMS_06 | US:106 | 1 | Understanding the microservices for project implementation | Rashmi Tiwari | 2020-05-02 | 2 days | 2 days | completed | 2 days | Learned the microservices from the trainers
|  | 2 | Created a git repository and understanding the team to work with git and analysis of case study and concepts of spring,requiremnet specification,agile concepts | Rashmi Tiwari | 2020-05-04 | 1 day | 1 day | completed | 1 day | A common git repository is created for collaboration among teammates and studied use cases,class diagram and their implementations to get better understanding
|  | 3 | designed class diagram,use cases,ER diagram | Rashmi Tiwari | 2020-05-05 | 1 day | 1 day | completed | 1 day | Observed the digaram and case studies ,according to it, test cases and pojo classes are created
|  | 4 | Test cases was implemented | Rashmi Tiwari | 2020-05-06 | 1 day | 1 day | completed | 1 day | prepared all the test cases involved in module
|  | 5 | Created pojo classes for modules ,entities design involved in modules with it | Rashmi Tiwari | 2020-05-07 | 1 day | 1 day | completed | 1 day | Implemeted all the classes and packages with specified details provided in the documentation
|  | 6 | Implemented user defined exception for the individual module | Rashmi Tiwari | 2020-05-08 | 1 day | 1 day | completed | 1 day | Performed all the crud operations using Layered wise architecture and exception are also implemented
|  | 7 | creation of rest controller,endpoints+validations, testing with postman | Rashmi Tiwari | 2020-05-11 | 1 day | 1 day | completed | 1 day | Implemented all the RESTAPIs and tested their working
|  | 8 | Angular UI , created angular components required in the assigned module, forms handling, | Rashmi Tiwari | 2020-05-12 | 1 day | 1 day | completed | 1 day | We used Angular6+
|  | 9 | Angular UI , created angular components required in the assigned module, forms handling with validations | Rashmi Tiwari | 2020-05-13 | 1 day | 1 day | completed | 1 day | We used Angular6+
|  | 10 | Angular UI, Introduced Service class which will interact with server side using httpclient ,observables can now be subscribed in components | Rashmi Tiwari | 2020-05-14 | 1 day | 1 day | completed | 1 day | We used Angular6+ ,Interacted with server side java
|  | 11 | Angular UI, Introduced Service class which will interact with server side using httpclient ,observables can now be subscribed in components | Rashmi Tiwari | 2020-05-15 | 1 day | 1 day | completed | 1 day | We used Angular6+ ,Interacted with server side java
|  | 12 | Individual server side modules are being converted into microservices,Discovery client is created | Rashmi Tiwari | 2020-05-16 | 1 day | 1 day | completed | 1 day | Discovery server is created for converting server side modules into microservices.
|  | 13 | code debugging and fixing is performed | Rashmi Tiwari | 2020-05-18 | 1 day | 1 day | completed | 1 day | Bug fixing is done for proper flow
|  | 14 | code debugging and Client side desiging improvement | Rashmi Tiwari | 2020-05-19 | 1 day | 1 day | completed | 1 day | Clent side desiging is improved
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.